## Gantt Data
Task | Start (Mon) | Duration (days) | Week Number | Status | Notes
S1 W1: No meeting (setup & orientation) | 2025-09-29 | 7 | 1 | Done
S1 W2: First meeting; discussed project | 2025-10-06 | 7 | 2 | Done
S1 W3: No progress (in San Francisco) | 2025-10-13 | 7 | 3 | Done
S1 W4: No progress (in San Francisco) | 2025-10-20 | 7 | 4 | Done
S1 W5: Aggregate papers; pick 3 meta-studies; meet supervisor | 2025-10-27 | 7 | 5 | In-Progress
S1 W6: Set MVP roadmap; checkpoints; pitfalls to avoid (Reading Week) | 2025-11-03 | 7 | 6 | Planned | Reading week
S1 W7: Start MVP implementation | 2025-11-10 | 7 | 7 | Planned
S1 W8: Continue MVP; measurable pre-Xmas goals | 2025-11-17 | 7 | 8 | Planned
S1 W9: Continue MVP; evaluate trajectory for Xmas | 2025-11-24 | 7 | 9 | Planned
S1 W10: MVP work; discuss results | 2025-12-01 | 7 | 10 | Planned
S1 W11: MVP work; discuss results; map S2 timeline; plan Xmas workload | 2025-12-08 | 7 | 11 | Planned
S1 W12: Buffer for previous weeks' work | 2025-12-15 | 7 | 12 | Planned