## neuromorphic_project_semester1_
Title | Semester | Task | Week Number | Start (Mon) | End (Fri) | Calendar End (Sun) | Duration (days) | Status | Notes
Neuromorphic Computing Project | 1 | S1 W1: No meeting (setup & orientation) | 1 | 2025-09-29 | 2025-10-03 | 2025-10-05 | 7 | Done
Neuromorphic Computing Project | 1 | S1 W2: First meeting; discussed project | 2 | 2025-10-06 | 2025-10-10 | 2025-10-12 | 7 | Done
Neuromorphic Computing Project | 1 | S1 W3: No progress (in San Francisco) | 3 | 2025-10-13 | 2025-10-17 | 2025-10-19 | 7 | Done
Neuromorphic Computing Project | 1 | S1 W4: No progress (in San Francisco) | 4 | 2025-10-20 | 2025-10-24 | 2025-10-26 | 7 | Done
Neuromorphic Computing Project | 1 | S1 W5: Aggregate research papers; pick 3 key meta-studies; discuss with supervisor | 5 | 2025-10-27 | 2025-10-31 | 2025-11-02 | 7 | In-Progress
Neuromorphic Computing Project | 1 | S1 W6: Reading Week (no classes): Plan MVP roadmap, milestones, pitfalls | 6 | 2025-11-03 | 2025-11-07 | 2025-11-09 | 7 | Planned | Reading week
Neuromorphic Computing Project | 1 | S1 W7: Start MVP implementation | 7 | 2025-11-10 | 2025-11-14 | 2025-11-16 | 7 | Planned
Neuromorphic Computing Project | 1 | S1 W8: Continue MVP; set measurable goals pre-Christmas break | 8 | 2025-11-17 | 2025-11-21 | 2025-11-23 | 7 | Planned
Neuromorphic Computing Project | 1 | S1 W9: Continue MVP; evaluate trajectory for Christmas | 9 | 2025-11-24 | 2025-11-28 | 2025-11-30 | 7 | Planned
Neuromorphic Computing Project | 1 | S1 W10: MVP work; discuss results | 10 | 2025-12-01 | 2025-12-05 | 2025-12-07 | 7 | Planned
Neuromorphic Computing Project | 1 | S1 W11: MVP work; discuss results; sketch Semester 2 timeline; plan Xmas workload | 11 | 2025-12-08 | 2025-12-12 | 2025-12-14 | 7 | Planned
Neuromorphic Computing Project | 1 | S1 W12: Buffer period for catch-up and stabilization | 12 | 2025-12-15 | 2025-12-19 | 2025-12-21 | 7 | Planned